LBT PROJECT

TECHNICAL SPECIFICATION

VERIFICATION PLAN AND ACCEPTANCE TESTS

| - Document No.: | - 401e036 |
| --- | --- |
| - Issue: | - c |
| - Date: | - August 25th., 1997 |
| - Prepared by: | - Gianpietro Marchiori/EIE |
| - Approved by: | - Gianpietro Marchiori/EIE |

INDEX

1.0 INTRODUCTION

1.1 Dimensional Checks

1.1.1 Overall dimensions of the telescope structure

1.2 Alignment Checks

1.3 Mass Checks

1.4 Functional Tests

1.4.1 Structure tests

1.4.1.1 Static testing of the telescope structure

1.4.1.2 Dynamic testing of the telescope structure (only assistance)

1.4.1.3 Balancing test of telescope

1.4.1.4 Jacking system tests

1.4.2 Test of hydrostatic bearing system (only assistance)

1.4.3 Test of the telescope drives (only assistance)

1.4.4 Test of the encoders (only on site)

1.4.5 Test of the cable wrap systems (only on site)

1.4.5.1 Test of the elevation cable drape

1.4.5.2 Test of the instrument cable wraps

1.4.6 Test of the brakes (only assistance)

1.4.7 Test of the auxiliary drives (with assistance of the drives’ supplier)

1.4.8 Test of the stow pins (with assistance of locking supplier)

1.4.9 Test of auxiliary equipment

1.4.10 Test of M1 covering systems (with assistance of the M1 covering supplier)

1.4.11 Tests of spiders

1.4.12 Tests of Safety Equipment

2.0 ACCEPTANCE TEST REVIEW

ANNEX

# 1.0	INTRODUCTION

The present document describes the main verifications to be performed on the telescope structure pre-erected both in factory (preliminary acceptance test) and on site, Mount Graham (final acceptance).

The preliminary acceptance test shall include:

- dimensional checks;

- alignment checks;

- mass checks and all

- functional tests

as specified in detail hereafter. The tests shall be done in the above given sequence.

The final acceptance tests, including mass dummies for the M1 mirrors, shall be performed after site erection and shall include:

- alignment checks and all

- functional tests

as specified hereafter.

The contractor is responsible for the definition and preparation of the procedures for each test of the preliminary acceptance. These procedures are subject to P.O. approval prior to start preliminary acceptance checks.

## 1.1	Dimensional Checks

For the preliminary acceptance of the telescope structure the contractor shall perform the measurements which are specified hereafter.

### 1.1.1	Overall dimensions of the telescope structure

Check of the following overall dimensions of the telescope structure, according to the telescope drawings.

- wHeight:	measured for azimuth ring level to the top supporting arms

- wWidth:	measured along the altitude axis from elevation platform end to end

- wWidth:	measured perpendicular to the altitude axis at the maximum extension

- wDiameter	of the azimuth ring and of the azimuth floor

The measurement accuracy shall be better than ± 1mm.

## 1.2	Alignment Checks

The contractor is responsible for the alignment of the telescope axes including the alignment of related subsystems like the hydrostatic bearing system and drive system.

The following verifications shall be carried out during the assembly activities and before the alignment checks, in compliance with the reference drawings:

- circularity and planarity of the azimuth ring

- circularity of each rolling sector

- parallelism of the rolling sectors

- runout of the central bearing

- level of azimuth frame

- encoder runout

For the preliminary acceptance of the telescope after the pre-erection in factory, the contractor has to demonstrate the accuracy of the location of the main telescope axes during operation of the structure, i.e. an elevation rotation angle of 98° and an azimuth rotation angle of 540°.

In particular the following alignment measurements shall be performed by the contractor for the preliminary acceptance of telescope:

- location of the altitude axis during rotation of the elevation structure from -0° to +90° zenith distance (maximum range -4° to +34°)

- location of the azimuth axes during rotation of the azimuth structure from -270° to +270°

- intersection point of the axes and

- perpendicularity of the axes

according to accuracy specifications for the axes, indicated on fig. No. 1.

## 1.3	Mass Checks

The contractor shall provide detailed parts lists of the telescope including all subsystems with mass evaluations, according to a breakdown prepared by the P.O.. Assembly masses shall be measured.

## 1.4	Functional Tests

All functional tests shall be performed in the factory for the preliminary acceptance.

### 1.4.1	Structure tests

#### 1.4.1.1	Static testing of the telescope structure

The tests which are described in this chapter shall be performed with the completely assembled telescope structure. The following static deformations due to gravity loading shall be measured by the contractors:

- rotation/yielding of the cells from horizontal to vertical position;

- deflection of the elevation structure with respect to the azimuth axis;

- deflection of spider swing arms

Measurements shall be taken at 0°, 30°, 60° and 90° and back to 0° with the same measurement steps. This cycle shall be performed twice.

The measurement accuracy shall be better or equal than ± 0.05mm.

#### 1.4.1.2	Dynamic testing of the telescope structure (only assistance)

For preliminary acceptance of the telescope after pre-erection in factory a dynamic response test of the structure shall be performed by the LBT P.O..

The purpose of the test is to measure the dynamic response (locked rotor resonance as well as higher resonances) in the open loop condition for the current loop of the telescope motors.

The verification of the lowest locked and free resonance frequencies can be done in the following way:

Excitation of the telescope axes with an electrical noise signal on the torque command input of the amplifiers and measuring the response of the telescope axis on the tachometer and by accelerometers. The input signal and response signal are fed to a frequency analyzer which produces a transfer gain and phase plot.

This test shall be performed for both elevation and azimuth drives.

#### 1.4.1.3	Balancing test of telescope

The friction torque of each axis shall be measured.

The balancing of the elevation structure shall be demonstrated in a test for the altitude angles from 0° to 90° in steps of 10° for the following combinations of spiders:

| SPIDER | INSTALL & TEST | DUMMY MASS |
| --- | --- | --- |
| F/15 Gregorian | Yes | No (only m2+cell) |
| M3 | Yes | No (only M3+cell) |
| Mirror Cover | Yes | No (only cover) |
| F/4 | No | Yes* |
| F/15 Cassegrain | No | No |
| F/25 Inner (G. Rieke) | No | No |

#### 1.4.1.4	Jacking system tests

The functionality of the elevation and azimuth jacking systems shall be verified by testing during the Azimuth frame assembly and with the full weight of the telescope.

### 1.4.2	Test of hydrostatic bearing system (only assistance)

The following performances of the hydrostatic bearing system shall be performed by the LBT P.O.:

- stability of the oil film thickness and of the oil temperature at the exit of the bearing pads in a duration test of 1 hour of continuous operation

- height of the oil meatus

- level of the vibrations induced by the system

- function of the system

- data transfer interface to the control system (status signals).

### 1.4.3	Test of the telescope drives (only assistance)

The following performances of the altitude and azimuth telescope drives shall be performed by the LBT P.O. for preliminary acceptance tests of the telescope:

- maximum rotation angles

- continuous and peak torque of the drives

- ripple and cogging torque

- speed range

- acceleration range

- surface temperature of the motor housing

- power amplifier: small signal bandwidth, slew rate, cross-over distortion, computer interface, EMI

A full load burn-in test shall be performed with both motors and amplifiers.

### 1.4.4	Test of the encoders (only on site)

The following performances of the altitude and azimuth telescope encoders shall be performed for final acceptance of the telescope:

- installation and tensioning of the encoder tapes

- absolute encoding accuracy over the whole rotation angle, i.e. ± 270° in azimuth and -4° to +94° in elevation axis

- resolution of the angular encoding over the whole rotation range as above

- repeatability of the encoding read-out and encoder initialization over the whole rotation ranges as specified above

- differential linearity

- read-out delay

- computer interface

- tachometer

### 1.4.5	Test of the cable wrap systems (only on site)

#### 1.4.5.1	Test of the elevation cable drape

The following performances of the elevation cable drape shall be performed for final acceptance of the telescope:

- angle difference during operation of the telescope

- maximum rotation angles of the cable drape

- friction measured at telescope axes when cable drape drive is disabled.

#### 1.4.5.2	Test of the instrument cable wraps

The following performances of the instrument cable wraps shall be performed for final acceptance of the telescope:

- angle difference during operation of the telescope

- maximum rotation angles of the cable wraps

- friction measured at telescope axes when cable wrap drive is disabled.

### 1.4.6	Test of the brakes (only assistance)

The following functional tests or measurements of the elevation and azimuth brakes shall be performed by the LBT P.O. for preliminary acceptance testing:

- maximum braking time

- maximum braking torque

- status signals - engaged/disengaged

### 1.4.7	Test of the auxiliary drives (with assistance of the drives’ supplier)

The following functional tests or measurements of the elevation and azimuth auxiliary drives shall be performed by the contractor for the preliminary acceptance testing:

- maximum torque

- maximum slewing speed

- maximum slewing range

- status signal - engaged/disengaged

### 1.4.8	Test of the stow pins (with assistance of locking supplier)

The following functional tests or measurements of the elevation locking systems shall be performed by the contractor for the preliminary acceptance testing:

- engagement of stow pins

- disengagement of stow pins

- manual function

- status signal - locked/unlocked

### 1.4.9	Test of auxiliary equipment

For the verification of the functions of the auxiliary equipment:

- access/handling/maintenance equipment

an inspection is envisaged by P.O.

### 1.4.10	Test of M1 covering systems (with assistance of the M1 covering supplier)

The following functional tests of the two M1 covering systems shall be performed for preliminary acceptance of the telescope:

- closing and opening time

- load conditions

- status signal open/closed

### 1.4.11	Tests of spiders

The following functional tests or measurements of the various spiders shall be performed by the contractor for the preliminary acceptance testing:

- alignment test

- functional test (only assistance)

- status signals (only assistance)

### 1.4.12	Tests of Safety Equipment

The following functional tests or measurements of the safety equipment shall be performed by the contractor for the preliminary acceptance testing:

- end stops

- limit switches

# 2.0	ACCEPTANCE TEST REVIEW

Acceptance Test Review shall be performed at the end of the acceptance tests.

The purpose of the Acceptance Test Review is to scrutinize the results of the previously performed acceptance tests.

The contractor shall predispose the relevant documents and draw up for each test performed the acceptance test certificate, to be signed by the contractor and by the P.O. responsible.

# ANNEX

Doc_info_start

Title: VERIFICATION PLAN AND ACCEPTANCE TESTS

Document Type: TECHNICAL SPECIFICATION

Source: EIE

Issued by: G.MARCHIORI

Date_of_Issue: 25/08/97

Revised by:

Date_of_Revision:

Checked by:

Date_of_Check:

Accepted by:

Date_of_Acceptance:

Released by:

Date_of_Release:

File Type:MS-WORD 6

Local Name: C0301/DOC/401e036c.doc

Category: TELESCOPE AZIMUTH FLOOR

Sub-Category: GENERAL TELESCOPE

Assembly: TELESCOPE TECHNICAL DOCUMENTS

Sub-Assembly: VERIFICATION PLAN AND ACCEPTANCE TESTS

Part Name:

CAN designation: 401e036

Revision: c

Doc_info_end